## Sheet1
Week | Module | Task ID | Task Description | Status
Week 1 | Project Setup | 1.1 | Finalize project title, scope, and objectives
Week 1 | Project Setup | 1.2 | Create GitHub repository and Overleaf document
Week 1 | Data Ingestion | 1.3 | Create folder structure and add sample PDFs
Week 1 | Data Ingestion | 1.4 | Implement PDF reader (ingest.py)
Week 1 | Data Ingestion | 1.5 | Implement text chunking (text_splitter.py)
Week 1 | Embedding | 1.6 | Research best embedding model (MiniLM / mpnet)
Week 1 | All | 1.7 | Push initial setup to GitHub
Week 2 | Embeddings + Retrieval | 2.1 | Implement embedding generation (embed_store.py)
Week 2 | Embeddings + Retrieval | 2.2 | Implement FAISS vector index and store chunks
Week 2 | Embeddings + Retrieval | 2.3 | Implement retrieval module (retriever.py)
Week 2 | Embeddings + Retrieval | 2.4 | Test retrieval accuracy with sample queries
Week 2 | Integration | 2.5 | Connect ingestion + embedding pipeline
Week 3 | Generation | 3.1 | Implement LLM query generator (generate.py)
Week 3 | Generation | 3.2 | Build Streamlit UI (app.py)
Week 3 | Generation | 3.3 | Integrate retrieval with generation
Week 3 | Logging | 3.4 | Implement database logging (db_logger.py)
Week 3 | Logging | 3.5 | Test query logging with UI inputs
Week 4 | Evaluation | 4.1 | Implement SQL analysis queries (evaluation.py)
Week 4 | Evaluation | 4.2 | Compute metrics (retrieval accuracy, latency, relevance)
Week 4 | Visualization | 4.3 | Plot results and visualize trends
Week 4 | Documentation | 4.4 | Write 3-page Overleaf report
Week 4 | Finalization | 4.5 | Upload final PDF, Excel, and code to GitHub